## Slide 1: BIMVET 3 BIM EXECUTION PLAN
BLOCK IV

## Slide 2
CONTENTS
  SECTION A: BIM EXECUTION PLAN OVERVIEW
    WHAT IS THE BIM EXECUTION PLAN?
    WHY IS THE BIM EXECUTION PLAN DONE?
    BIM EXECUTION PLAN COMPONENTS
  SECTION B: PROJECT INFORMATION
  SECTION C: PROJECT GOALS / BIM USES
    MAJOR BIM GOALS / OBJECTIVES
    BIM USES
  SECTION D: ORGANIZATIONAL ROLES / STAFFING
  SECTION E: BIM PROCESS AND STRATEGY
  SECTION F: BIM EXCHANGE PROTOCOL AND SUBMITTAL FORMAT
  SECTION G: BIM DATA REQUIREMENT
  SECTION H: COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
    COLLABORATION STRATEGY
    DISCIPLINE MODEL REQUIREMENTS
  SECTION I: QUALITY CONTROL
  SECTION J: TECHNOLOGY INFRASTRUCTURE & SOFTWARE
BLOCK IV

## Slide 3
SECTION A
BIM EXECUTION PLAN OVERVIEW
BLOCK IV

## Slide 4
SECTION A: BIM EXECUTION PLAN OVERVIEW
  WHAT IS THE BIM EXECUTION PLAN?
  Building Information Modeling (BIM) is the process of creating and managing information about a construction project throughout its entire lifecycle. In other words, BIM is basically a different way of creating, using and sharing building lifecycle data [1].
Figure 1: What is BIM? What does it do? (URL-1)
BLOCK IV

## Slide 5
SECTION A: BIM EXECUTION PLAN OVERVIEW
  WHAT IS THE BIM EXECUTION PLAN?
  BIM Execution Plan is a plan that defines the objectives of implementing BIM technology in a project. Explains how to apply the created model, explains the application processes and ways of information exchange. It also contains information about all the project infrastructure necessary for a successful BIM implementation, namely the technologies we will implement, the team responsible for the implementation, and the contracts to be fulfilled [2].
Figure 2: BIM Community The BIM Execution Plan (URL-2)
BLOCK IV

## Slide 6
SECTION A: BIM EXECUTION PLAN OVERVIEW
  WHAT IS THE BIM EXECUTION PLAN?
  It should be noted that there is no universal BIM application method for every project. Each team should effectively design a well-tailored BEP implementation strategy. Therefore, only the team that understands the project's goals, characteristics and capabilities of its members can effectively implement BIM in the project. After creating the plan, the team should monitor progress against the plan. Continuously developing, updating and correcting the plan at every stage of the project is crucial to obtain maximum benefit from BIM implementation [2].
BLOCK IV

## Slide 7
SECTION A: BIM EXECUTION PLAN OVERVIEW
  WHY IS THE BIM EXECUTION PLAN DONE?
  One way to streamline the BIM implementation process on a project in an organized and efficient way is to create a BIM Execution Plan (BEP) before starting the design phase[1].
BLOCK IV
Figure 3: (URL-3)

## Slide 8
SECTION A: BIM EXECUTION PLAN OVERVIEW
  WHY IS THE BIM EXECUTION PLAN DONE?
  The BEP is a procedural process that outlines the overall vision of the project with implementation details for the project team to follow throughout the project. It also helps the employer and project members document the BIM deliverables and processes agreed for the project and defines roles and responsibilities for each of these deliverables [3].
  By increasing the level of planning, the number of uncertainties in the implementation process is reduced and thus the overall risk for all parties involved in the project is reduced [2].
BLOCK IV

## Slide 9
SECTION A: BIM EXECUTION PLAN OVERVIEW
  BIM EXECUTION PLAN COMPONENTS
  BEP; It should express the scope of BIM implementation, the process flow for BIM tasks, and information exchange between parties, as well as describe the project and company infrastructure necessary to support implementation[4].
  Defining project information,
  Determining the project BIM targets,
  Choosing BIM uses,
  Creating a BIM process,
  Defining how to exchange information,
  Choosing the right infrastructure.
BLOCK IV

## Slide 10
SECTION B
PROJECT INFORMATION
BLOCK IV

## Slide 11
SECTION B: PROJECT INFORMATION
  This section; It is the section that contains information about the project such as the name of the project, the owner of the project, the short project description, the stages of the project.
  PROJECT OWNER
  PROJECT NUMBER
  PROJECT NAME
  PROJECT LOCATION AND ADDRESS
  BRIEF PROJECT DESCRIPTION
  PROJECT SCHEDULE / PHASES
BLOCK IV

## Slide 12
SECTION B: PROJECT INFORMATION
  Necessary information can be given as in Table 1.
BLOCK IV

## Slide 13
SECTION B: PROJECT INFORMATION
BLOCK IV
  In addition, when each stage in the project will start and when it will end should be indicated with a table.

## Slide 14
SECTION C
PROJECT GOALS / BIM USES
BLOCK IV

## Slide 15
SECTION C: PROJECT GOALS / BIM USES
  MAJOR BIM GOALS / OBJECTIVES
  The second step in creating an effective BIM Execution Plan is to consider the benefits that BIM can bring to our project and to define the goals we aim to achieve on this basis. To effectively define goals, such goals must be relevant to the project being created, measurable, and achievable for the project team.
BLOCK IV

## Slide 16
SECTION C: PROJECT GOALS / BIM USES
  MAJOR BIM GOALS / OBJECTIVES
  In addition, since the objectives of the BEP will vary depending on the project characteristics, they should be considered separately for each project .
BLOCK IV
  The objectives of the project can be given in a table.

## Slide 17
SECTION C: PROJECT GOALS / BIM USES
  MAJOR BIM GOALS / OBJECTIVES
  The table may also include potential BIM Uses.
BLOCK IV

## Slide 18
SECTION C: PROJECT GOALS / BIM USES
  BIM USES
  When choosing BIM uses, we need to consider our goals for the project and the results we want. We include the BIM uses we have determined in this section by marking them in the table.
BLOCK IV

## Slide 19
SECTION C: PROJECT GOALS / BIM USES
  BIM USES
BLOCK IV
  BIM usages in the table are written as an example.

## Slide 20
SECTION D
ORGANIZATIONAL ROLES / STAFFING
BLOCK IV

## Slide 21
SECTION D: ORGANIZATIONAL ROLES / STAFFING
  Figure 4 shows the synthesis of individual disciplines and multidisciplinary integration. This section defines the roles and responsibilities of team members. These teams should consist of technical staff experienced in BIM modeling tools in their fields of expertise (architectural, structural, mechanical, electrical, etc.). It differs for each project. It is organized according to the disciplines that should be in the project team.
  The tasks of each expert within the scope of the project should be defined in articles.
PROJECT NAME
MECHANICAL ENGİNEERS
(ME)
CONSTRUCTION MANAGERS
(CM)
STRUCTURAL ENGİNEERS
(SE)
LIGHTING/ ELECTRICAL ENGINEERS
(LE)
Figure 4: Project Team.
BLOCK IV

## Slide 22
SECTION D: ORGANIZATIONAL ROLES / STAFFING
  Construction Manager
  BIM Execution Plan
  Site Investigation
  Constructability Input
  Preliminary Estimate
  Preliminary Schedule
  Final Estimate
  Final Schedule
  4D Modelling
BLOCK IV
  Structural Engineer
  Geotechnical Report
  Preliminary Base Model
  Structural Systems Options
  Structural System Selection
  Preliminary Structural System Design
  Final Structural System Design
  Mechanical Engineer
  Mechanical System Options
  Mechanical System Space Requirements
  Mechanical System Selection
  Preliminary Mechanical System Design
  Final Mechanical Design
  Lighting/ Electirical
  Engineer
  Daylighting Options
  Lighting/Electirical System Selection
  Preliminary System Design
  Site Lighting Design
  Energy Model Review
  Final Electirical Design
  Update Energy Model
  This figure displays the individual disciplines’ specific tasks.
  The center circle shows the synthesis of multidisciplinary integration.
  Multidisciplinary Integration
Figure 5: Organizational Roles and Responsibilities.

## Slide 23
SECTION E
BIM PROCESS AND STRATEGY
BLOCK IV

## Slide 24
SECTION E: BIM PROCESS AND STRATEGY
  In this section, “Team Process Overview Map” and “Detailed Team Member Process Map” are prepared.
  A process map is a planning and management tool that visually describes the flow of work.
  The Process Map template is a valuable tool for documenting, analyzing, and better understanding your project team's business processes and associated results.
  The Process Map template should be organized according to stages, which you can use to record the goals, activities and outputs of each stage in your project process.
  It enables you to improve your team's organization, productivity and communication by reaching a common understanding of all kinds of processes.
BLOCK IV

## Slide 25
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Figure 6: BIM Process Map (5).
Figure 7: BIM Use Map (5).

## Slide 26
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Figure 8: BIM Process Map (5).

## Slide 27
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Figure 9: Team Overall Process Map (6).

## Slide 28
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
All Team Members
Construction Managers
Structural Engineers
Mechanical Engineers
Lighting/ Electirical Engineers
  The sample table shows the common meeting times for all team members shown in purple for the integration of BIM outputs. Other tones indicate individual discipline meeting times.
Figure 10: Weekly Meeting Schedule (6).

## Slide 29
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Construction Managers
Structural Engineers
Mechanical Engineers
Lighting/ Electirical Engineers
Figure 11: :Team General Process Map (6).

## Slide 30
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Figure 12: :Lighting/ Electrical Engineer General Process Map (6).

## Slide 31
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Figure 13: :Structural Engineer General Process Map (6).

## Slide 32
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Figure 14: :Mechanical Engineer General Process Map (6).

## Slide 33
SECTION E: BIM PROCESS AND STRATEGY
  Sample process maps prepared in studies in the literature.
BLOCK IV
Figure 15: :Construction Manager General Process Map (6).

## Slide 34
SECTION F
BIM EXCHANGE PROTOCOL AND SUBMITTAL FORMAT
BLOCK IV

## Slide 35
SECTION F: BIM EXCHANGE PROTOCOL AND SUBMITTAL FORMAT
  This section describes each of the team's uses of BIM and the result of each (Table 4). With the Team General Process Map, the duration of each BIM use is summarized according to the stages (Table 5). In addition, the files to be delivered are determined in which format (pdf, dwg, etc.) the 2D layouts will be presented, as well as the original program formats in which the data were prepared.
BLOCK IV

## Slide 36
SECTION F: BIM EXCHANGE PROTOCOL AND SUBMITTAL FORMAT
BLOCK IV
  BIM usages in the table are written as an example.

## Slide 37
SECTION G
BIM DATA REQUIREMENT
BLOCK IV

## Slide 38
SECTION G: BIM DATA REQUIREMENT
  This Data Environment is a common database for all project information and documents. It allows sharing of projects and technical documents and controlling their revisions, tracking all correspondence on a common system and sharing data. All project documents (2D drawings, quantity studies, etc.) to be prepared within the scope of BIM processes must be produced in accordance with the Common Data Environment (Project Management System).
BLOCK IV

## Slide 39
SECTION H
COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
BLOCK IV

## Slide 40
SECTION H: COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
  COLLABORATION STRATEGY
  This section should include the following.
  Weekly meeting schedule – time
  Team communication – Google Docs, common file storage
  Continual interdisciplinary interaction for building systems’ integration
  Team leaders selected based on project phase
  Meeting minutes issued and discussed after each meeting to accomplish team objectives by next meeting date.
BLOCK IV

## Slide 41
SECTION H: COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
  DISCIPLINE MODEL REQUIREMENTS
  In the BIM Implementation Plan, mandatory information requirements are defined depending on the scope of the Project. These;.
  Architectural Model Requirements
  Structural Model Requirements
  Mechanical Model Requirements
  Electrical and Electronic Model Requirements
BLOCK IV

## Slide 42
SECTION H: COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
  DISCIPLINE MODEL REQUIREMENTS
  Architectural Model Requirements: Doors, windows, elevators, escalators, screens, turnstiles, furniture, lighting elements, routing elements, MEP equipment, etc. It is defined which information will be given for all building elements and all materials used.
BLOCK IV
Figure 16: (URL-4)

## Slide 43
SECTION H: COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
  DISCIPLINE MODEL REQUIREMENTS
  Structural Model Requirements: Reservations on vertical/horizontal circulation elements, all shafts, spaces, stairs, carrier elements are processed into the BIM model with their brief explanations.
BLOCK IV
Figure 17: (URL-5)

## Slide 44
SECTION H: COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
  DISCIPLINE MODEL REQUIREMENTS
  Mechanical Model Requirements: The width, height and height information of the elements of the systems are modeled as 3D parametric.
BLOCK IV
Figure 18: (URL-6)

## Slide 45
SECTION H: COLLABORATION PROCEDURES AND METHOD TO HANDLE SHARED MODELS
  DISCIPLINE MODEL REQUIREMENTS
  Electrical and Electronic Model Requirements: All generators, transformers, cable trays, fixtures, switches, sockets, announcements, telephones, passenger information screens, card readers, detectors, etc. in the project. Medium voltage, Direct voltage and Low voltage etc. The main equipment of all systems are shown in the model.
BLOCK IV
Figure 19: (URL-7)

## Slide 46
SECTION I
QUALITY CONTROL
BLOCK IV

## Slide 47
SECTION I: QUALITY CONTROL
  The project owner is responsible for the quality of all models to be presented. First, the disciplines should check the model quality within themselves. The BIM manager is responsible for controlling the quality of the model, taking into account the coordination of all disciplines, within the framework of its defined responsibilities. In this section, checklists are first created within the scope of the BIM Execution Plan and models are evaluated according to this list.
BLOCK IV

## Slide 48
SECTION J
TECHNOLOGY INFRASTRUCTURE & SOFTWARE
BLOCK IV

## Slide 49
SECTION J: TECHNOLOGY INFRASTRUCTURE & SOFTWARE
  In this section, the provision of a cloud system or main server, the installation of infrastructure that provides instant access to all projects, and the installation of the infrastructure, and the hardware features of the system are determined.
  In addition, in order to avoid the problem of opening the models between the Designer and the Manufacturer, which is not possible due to the revision difference during the project, which version of the same software the Designer and the Manufacturer (Consultant/Administration, Contractor, Sub-contractors, etc.) will use is determined at the beginning of the work and explained in this section. When an update is required, for which software, how and under whose responsibility (Designer/Manufacturer) the software will be updated is described in the BIM Implementation Plan.
BLOCK IV

## Slide 50
REFERENCES
J. A. Ramírez-Sáenz, J. M. Gómez-Sánchez, J. L. Ponz-Tienda, J. P. Romero-Cortés and L. Gutiérrez-Bucheli, (2018). “Requirements For a BIM Execution Plan (BEP): A Proposal For Application in Colombia”. Building & Management, vol. 2(2), pp. 05-14.
Lozinski, I. (2020). “Creating a successful BIM Execution Plan: Part 1”, https://bimcorner.com/creating-a-successful-bim-execution-plan-part-1/ (erişim tarihi: 07.07.2021).
Building and Construction Authority, (2013). “Singapore BIM Guide - V2.0,” Cornet, pp. 1–70.
Hrdina, O., Matějka, P., (2016). “Bım Execution Plan in Czech Republic”. journal Business & IT, 2, pp:17-23.
Lozinski, I. (2020). “Creating Successful BIM Execution Plan. Part 3: Design A BIM Process”, https://bimcorner.com/creating-successful-bim-execution-plan-part-3-design-a-bim-process/ . (erişim tarihi: 07.07.2021).
Byard, A. & LaChance, B. (2012). “ Building Information Modeling Project Execution Plan”, …..
URL1: https://www.google.com/search?q=building+information+modelling&tbm=isch&ved=2ahUKEwi5sa2Tkov0AhXLxrsIHTc1ATYQ2-cCegQIABAA&oq=BU%C4%B0LD%C4%B0NG+%C4%B0NFORMAT%C4%B0ON+MODELL%C4%B0NG&gs_lcp=CgNpbWcQARgAMgcIIxDvAxAnMgUIABCABDIGCAAQBxAeMgYIABAHEB4yBggAEAcQHjIECAAQHjIECAAQHlAAWABg1w1oAHAAeACAAZYBiAGWAZIBAzAuMZgBAKoBC2d3cy13aXotaW1nwAEB&sclient=img&ei=w1aKYfnDKcuN7_UPt-qEsAM&bih=912&biw=1920&rlz=1C1EJFC_enTR844TR844#imgrc=7HPwvz9GqsSITM
URL2:https://www.google.com/search?q=bim+execution+plan&rlz=1C1EJFC_enTR844TR844&sxsrf=AOaemvLeGPjhlRCwkXATjnIpiBSTw3B94g:1636456425769&source=lnms&tbm=isch&sa=X&sqi=2&ved=2ahUKEwi2xMqfk4v0AhW7kWoFHWJIDfAQ_AUoAXoECAEQAw&biw=1920&bih=912&dpr=1#imgrc=Yxmh1NPVdhtmAM
URL3: https://tr.pinterest.com/pin/785033778792647997/
URL4: https://tr.pinterest.com/pin/367113807132555563/
URL5: https://tr.pinterest.com/pin/672091944396019969/
URL6: https://tr.pinterest.com/pin/172614598208917741/
URL7: https://tr.pinterest.com/pin/772648879820699523/
BLOCK IV